## Sheet1
Milestone Review Per Schedule
Milestone | Expected Date | Completed Date | Completed? (Yes/No/Pending) | Reason (if milestone was not met)
Brainstorm with client on project | 2020-09-04 | 2020-09-04 | Yes | n.a
Design review meeting with instructor | 2020-09-25 | 2020-09-25 | Yes | n.a
Present and dicuss use cases/requirements with client | 2020-10-02 | 2020-10-02 | Yes | n.a
Present main page and theme to client | 2020-10-16 | 2020-10-16 | Yes | n.a
Present rough draft of site to client | 2020-10-30 | 2020-10-30 | Yes | n.a
Implement the rest of the pages on site | 2020-11-07 | 2020-11-08 | Yes | n.a
Present finalized site (with any changes suggested from client) and dicuss future work | 2020-11-13 | n.a | No | Due to the individual project now being due on 11/24, I will change the 11/13 meeting to one where I ask for the client's feedback, moving this proposed milestone to 11/20/2020
Project submission | 2020-11-24 | n.a | Pending | Individual project has not been submitted yet