## Sheet1
Milestone Review Per Schedule
Milestone | Expected Date | Completed Date | Completed? (Yes/No/Pending) | Reason (if milestone was not met)
Brainstorm with client on project | 2020-09-04 | 2020-09-04 | Yes | n.a
Design review meeting with instructor | 2020-09-25 | 2020-09-25 | Yes | n.a
Review use cases & requirements with client | 2020-10-02 | 2020-10-02 | Yes | n.a
main page and theme idea for website | 2020-10-16 | 2020-10-16 | Yes | n.a
Hosted main page and skeleton for site | 2020-10-30 | 2020-10-30 | Yes | n.a
Near complete hosted website | 2020-11-07 | 2020-11-08 | Yes | n.a
Working website with presentation slides | 2020-11-24 | 2020-11-22 | Yes | n.a